| Item | Start Date | Task | Responsible Officer(s) | Due date | Status | Notes/Comments |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Early May | Submit ministerial request for any end of year actions that require Treasurer’s approval under the Financial Management Act 1995 including, but not limited to: - Treasurer’s advance - Gifting - Write-offs, waivers, postponements - Ex-gratia payments - Transfers of appropriation (between agencies or types) |  | Last working day in May | ⚪ Not started 🔵 In progress 🟢 Complete |  |
|  | Early June | May hard close: - Prepare reconciliations for all required balances and perform variance analysis - Review General Ledger and financial statements (ie negative amounts, incorrect SDC’s, use of prior period errors, Territory revenue balances etc) - Resolve discrepancies |  | End June |  |  |
|  | Pre-30 June | Agency Proforma - Review financial statements (including notes) proforma for changes to presentation or accounting standards - Implement any necessary changes to workplan and workpapers |  | End June |  |  |
|  | Pre-30 June | Set up electronic TRM and LAN folders for end of financial year work papers |  | End June |  |  |
|  | Pre-30 June | Liaise with AG to determine audit dates and entry meeting. Update workplan for revised dates. |  |  |  |  |
|  | Pre-30 June | Allocate all tasks on workplan and advise affected staff. |  |  |  |  |
|  | End June | Send related party disclosure questionnaires, policy and guidance documents to seek declarations from agency KMP. |  | Early July |  |  |
|  | Pre-30 June | Liaise with DCDD Fixed assets to adjust for asset revaluations |  | 30 June |  |  |
|  | 30 June | Close off for period 12 journals – GAS. |  |  |  |  |
|  | Period 14 | Process end of year journals for: |  | End of Period 14 |  |  |
|  |  | Clear CRCA, clearing and suspense accounts |  |  |  |  |
|  |  | Accrued expenses and accounts payable |  |  |  |  |
|  |  | Revenue recognition and unearned revenue balances |  |  |  |  |
|  |  | Employee entitlements |  |  |  |  |
|  | Period 14 | Prepare reconciliations and analytical analysis for all operating statement and balance sheet line items. Refer to reconciliation workplan |  | End of Period 14 |  |  |
|  | Period 14 | Process any rectification journals as identified in reconciliations as required |  | End of Period 14 |  |  |
|  | Period 14 | Finalise reconciliations and analytical analysis for all operating statement and balance sheet line items |  | End of Period 14 |  |  |
|  | Period 14 | CFO or equivalent to review and sign-off reconciliations and analytical analysis |  | End of Period 14 |  |  |
|  |  | Treasury Return: Agency June budget vs actuals with comments |  |  |  |  |
|  |  | Audit/end of year to commence |  |  |  |  |
|  |  | Agency financial information to auditors |  | End July |  |  |
|  | July | Draft financial statements (including notes to the financial statements) |  | Mid-August |  |  |
|  | July | Treasury Return: Gifts, write-offs, postponements, waivers and ex-gratia payments |  | As per Circular (Typically end July) |  |  |
|  | July | Treasury Return: Receivables |  | As per Circular (Typically end July) |  |  |
|  | July | Treasury Return: Advances and investments |  | As per Circular (Typically end July) |  |  |
|  | July | Treasury Return: Contingent liabilities |  | As per Circular (Typically end July) |  |  |
|  | July | Treasury Return: Commitments |  | As per Circular (Typically end July) |  |  |
|  | July | Treasury Return: Fraud reporting |  | As per Circular (Typically end July) |  |  |
|  | July | Treasury Return: Commercial insurance register |  | As per Circular (Typically end July) |  |  |
|  | July | Treasury Return: Revenue disclosures |  | As per Circular (typically early Aug) |  |  |
|  | July | Treasury Return: Leases disclosures |  | As per Circular (typically early Aug) |  |  |
|  | July | Treasury Return: COFOG-A actual disclosures |  | As per Circular (typically mid Aug) |  |  |
|  | Mid-August | CFO or equivalent to review and sign-off financial statements |  | End August |  |  |
|  |  | Financial statements sign-off |  | As per Circular (typically last working day August) |  | CE and CFO (or equivalent) to sign-off: - Financial statements (including notes to the financial statements) - APEX generated financial statements - TAFR Representation letter Sign off needs to be forwarded to your DTF Financial Analyst and emailed to: FMG-TAFRCoordination.ntt@nt.gov.au |
|  |  | Agency representation letter to Minister |  |  |  |  |
|  | Oct | Annual report tabled in the Legislative Assembly. |  | October Sittings |  |  |