# Major works project variation process outside the budget development process

Client agency and or construction authority identify a project variation requirement

Construction authority to prepare a submission to the Budget Review Sub-committee (BRS), identifying requirement for additional funding, or identifying deferral of another project. Submission to include cover sheet from the construction authority

Cabinet to ratify BRS decision

BRS reviews proposal and advises if project supported, funding approach and or which project/s to be deferred

Accountable officer of construction authority can approve the variation

Is there external funding or substitution from minor works, repairs and maintenance or other operational funding offered to fully fund the project variation?

No

Yes

Construction authority must obtain agreement from the accountable officer of the relevant client agency (or agencies) and notify DTF within 10 working days from date of signed agreement between the accountable officers of the construction authority and relevant client agency (or agencies)

DTF actions program variation

Is there a previous immaterial variation already approved for the same project?

Yes

No

Does the substitution offered come from:

- external funding

- other operational funding

- or minor works or repairs and maintenance where variation will result in the transfer of funding or allocation from the infrastructure program of one agency to another?

Construction authority must notify DTF and relevant client agency within 10 working days from approving the project variation.

No

Yes

Is the variation less than or equal to 10 per cent of the approved program or $250,000 (immaterial variation), whichever is the lesser?

Yes

No